## Cool Spine
Cool Spine |  | Year 1 | [26 empty] | Year 2
Generated from roadmap.yaml |  | Q1 2026 | [6 empty] | Q2 2026 | [5 empty] | Q3 2026 | [6 empty] | Q4 2026 | [6 empty] | Q1 2027 | [5 empty] | Q2 2027 | [5 empty] | Q3 2027 | [6 empty] | Q4 2027
 | time axis 2026-01-01 to 2027-10-07
Workstream / Task | Status
Preperation | Epic
Planning & Preparation | Done
Discussion with CoolSpine Team | Done
Medical Device Design course project kickoff | Done | bar: 2026-01-01
Team Established | Done | bar: 2026-01-01
Onsite with Sage PD – detailed project review and establishment of responsibilities | Done | bar: 2026-01-01
Establishment of design Functional Requirements | Done | bar: 2026-01-15
Course 2.75 - Final presentations | Done | bar: 2026-01-15
Strategy Presentations | Done | bar: 2026-01-15
Studied refrigeration v. thermoelectric cooling | Done | bar: 2026-01-29
Reviewed Zoll system | Done | bar: 2026-01-29
New task | Done
Concept Presentation | Epic
De-selection of thermoelectric cooling | Done | bar: 2026-01-29
Hub connector review with Sage | Done | bar: 2026-02-12
Modelling of worst-case maximum cooling | Done | bar: 2026-02-12
Fabrication and assembly of test fluid cooling loop | Done | bar: 2026-02-12
Testing | Done | bar: 2026-02-12
Preliminary UIUX, including pump controls and alarms | Done | bar: 2026-02-26
Full system concept design established | Done | bar: 2026-02-26
Model of required cooling power and cooling power v time | Done | bar: 2026-02-26
Bench testing | Done | bar: 2026-02-26
Course 2.75 - Final presentations | Done | bar: 2026-02-26
Thermistor selection & meeting with Sage and Amphenol | Done | bar: 2026-03-12
Assembly of pressure and temperature sensing modules | Done | bar: 2026-03-12
Finalization of UIUX | Done | bar: 2026-03-12
Risk & DMEA Review with Sage | Done | bar: 2026-03-26
Onsite catheter testing at MIT with Sage | Done | bar: 2026-03-26
Revision of cooling system design to support cartridge design | Done
Preliminary discussion with Aspen | Done | bar: 2026-03-26
Propane R290, Check with Aspen (supplier) if the gas we are using may be used in the operating room, and if they have any experience with it in medical devices | In progress
Catheter test to failure | Done | bar: 2026-03-26
Catheter power | Epic
Analytical Model creation - catheder to tissue (to be verified) | Done
Cathether design fixed (SAGE) | Done
Cool plates and cartrige design | Future
Banchmark catheder test (body phantom) 0C -> 40W at y ml/min | Future
Termistors study | In progress
Cartrige | Epic
Analytical Model creation | Done
Manufacture a 3d printed cartrige | Done
Test in ice bath | Done
Test with cool plate system ? | Done
Cooling System | Future
Current coldplate (-2-1) testing -> -27W | Future
Tuning of the current system | In progress
CONTINGENCY PLAN (if we need: bigger coldplate, 10weeks - 10K ?) | Future | bar: 2026-11-05
CONTINGENCY 2 (think about peltier ...) | Future
order second cartrige from "R&D" | In progress
Test the second cartrige | Future | bar: 2026-11-05
V2 - including the deboubler ? | Future | bar: 2026-11-19 to 2026-12-03
Manufacture final cartrige from selected material | Future
Tubing | Epic
Conduct test with the Tygoon PVC (10% drop at after 20min) | Future
Conduct tests for the current tubing, moving it along the length every 30min | In progress
Identify alternate tubing | Future
Test & Verify | In progress
masterflex qualified sesrs | Future | bar: 2026-11-05
3 materials: 6h approriate temp and flowrate, closed lines, | Future | bar: 2026-11-05
reach out to 2 different tubing companies | Future | bar: 2026-11-05
move charges venture well | Future | bar: 2026-11-19
use silicon caulking | Future | bar: 2026-11-19
create new sensors Tshaped connectors | Future | bar: 2026-11-05
Housing P1.5 | Epic
CAD modeling | Done
Order | Done | bar: 2026-09-24 to 2026-10-08
Build | In progress | bar: 2026-10-22 to 2026-11-05
Assemble & Verify | Future | bar: 2026-11-05
Probes | Epic
Evaluate probes from previous work --> probes insufficient --> new probes required | Future
Design | Future
Manufacture | Future
Test & Integrate | Future
Design new probes for the animal study | In progress
Order needls and extension cables | In progress
Integrate and test the probes | Future | bar: 2026-11-05
WIRE THE Peristaltic pump limit switch | Future | bar: 2026-11-05
Liquid level sensor | Future
Try the sensro we allready have | Future
Send a quote | Future
Dboubler | Future
Circut Board | Epic
Design | Done | bar: 2026-09-24 to 2026-10-08
Order | Done | bar: 2026-10-08
Integrate & Test | In progress
Revise | Future | bar: 2026-11-05 to 2026-12-03
Battery System | Epic
Integrate the Battery | In progress
Implement UI and Error cases | In progress
Test | In progress
Simulate 30min operation | Future | bar: 2026-11-05
Test whether USB-C input is an option | In progress
Sage Test Setup | Epic
Design and order | Future
Build | Future
Prep for Animal Study | Epic
Study previous experiments | In progress | bar: 2026-10-08 to 2026-11-05
Make contact with the Ohaio people | In progress
Desing the Study protocol - especially probe placement | Future
Freeze the software/hardware version and conduct final verification | Future
Software | Future
Move the repos to mit hosted Github | In progress
Review the falut codes and connect to the error code excel | In progress
Reverse Enginginerg of the early criolife prototype | In progress
Intellectual Property | Epic
Internal Innovation Review - ID potential new IP | Future
Review pertinent prior art | Future
Review prior art | Future
Submit IP disclosure | Future
Documentation | Future
Build documentation package | Future
Identify next potential partners | Future
Conduct tranfer | Future
Create protokoll | Future
conducts | Future
Testing | Future
Sous vide | In progress | bar: 2026-09-24 to 2026-11-05
bain marie test | Future | bar: 2026-11-05 to 2026-12-03
GLP Animla Study | Future
Electromagnetic compatibility testing | Future | bar: 2027-01-14 to 2027-01-28
Milestones | Epic
Cadaver Test | Milestone | bar: 2026-12-17
Non GLP Animal Study | Milestone
Note on B4: Done, In progress, and Future come from roadmap.yaml. Epic marks a section. Milestone marks a single date. Green cells are the sprints a task covers. A blue cell is the sprint that contains a milestone.