## Cool_Spine_Roadmap_October_2026
|  | Year 1 | [26 empty] | Year 2
|  | Q1 2026 | [6 empty] | Q2 2026 | [5 empty] | Q3 2026 | [6 empty] | Q4 2026 | [6 empty] | Q1 2027 | [5 empty] | Q2 2027 | [5 empty] | Q3 2027 | [6 empty] | Q4 2027
 | time axis 2026-01-01 to 2027-10-07
Workstream / Task | Sprint Filter
Preperation | Epic
Planning & Preparation
Discussion with CoolSpine Team | Next Sprint
Medical Device Design course project kickoff | bar: 2026-01-01
Team Established | Next Sprint | bar: 2026-01-01
Onsite with Sage PD – detailed project review and establishment of responsibilities | Current Sprint | bar: 2026-01-01
Establishment of design Functional Requirements | bar: 2026-01-15
Course 2.75 - Final presentations | Epic | bar: 2026-01-15
Strategy Presentations | bar: 2026-01-15
Studied refrigeration v. thermoelectric cooling | bar: 2026-01-29
Reviewed Zoll system | bar: 2026-01-29
Concept Presentation | Epic | bar: 2026-01-29
De-selection of thermoelectric cooling | bar: 2026-01-29
Hub connector review with Sage | bar: 2026-02-12
Modelling of worst-case maximum cooling | bar: 2026-02-12
Fabrication and assembly of test fluid cooling loop | bar: 2026-02-12
Testing | bar: 2026-02-12
Preliminary UIUX, including pump controls and alarms | bar: 2026-02-26
Full system concept design established | bar: 2026-02-26
Model of required cooling power and cooling power v time | bar: 2026-02-26
Bench testing | bar: 2026-02-26
Course 2.75 - Final presentations | bar: 2026-02-26
Thermistor selection & meeting with Sage and Amphenol | bar: 2026-03-12
Assembly of pressure and temperature sensing modules | bar: 2026-03-12
Finalization of UIUX | bar: 2026-03-12
Risk & DMEA Review with Sage | bar: 2026-03-26
Onsite catheter testing at MIT with Sage | bar: 2026-03-26
Revision of cooling system design to support cartridge design | bar: 2026-03-26
Preliminary discussion with Aspen | bar: 2026-03-26
Check with Aspen (supplier) if the gas we are using may be used in the operating room, and if they have any experience with it in medical devices | Current Sprint | bar: 2026-10-22
Catheter test to failure | bar: 2026-03-26
Catheter power | Epic
Analytical Model creation - catheder to tissue (to be verified)
Cathether design fixed (SAGE)
Cool plates and cartrige design
Banchmark catheder test (body phantom) 0C -> 40W at y ml/min
Current coldplate (-2-1) testing -> -27W
Tuning of the current system
CONTINGENCY PLAN (if we need: bigger coldplate, 10weeks - 10K ?)
CONTINGENCY 2
Cartrige | Epic
Analytical Model creation
Manufacture a 3d printed cartrige
Test in ice bath
Test with cool plate system ?
Cooling System
Tubing | Epic
Conduct test with the Tygoon PVC (10% drop at after 20min)
Conduct tests for the current tubing, moving it along the length every 30min | Current Sprint | bar: 2026-10-22
Identify alternate tubing
Test & Verify
Housing P1.5 | Epic
CAD modeling
Order
Build
Assemble & Verify
Probes | Epic
Evaluate probes from previous work --> probes insufficient --> new probes required
Design
Manufacture
Test & Integrate
Design new probes for the animal study | Current Sprint | bar: 2026-10-22
Integrate and test the probes | Next Sprint | bar: 2026-11-05
Circut Board | Epic
Design
Order
Integrate & Test
Revise
Battery System | Epic
Integrate the Battery
Implement UI and Error cases
Test
Simulate 30min operation
Test whether USB-C input is an option | Current Sprint | bar: 2026-10-22
Sage Test Setup | Epic
Design and order
Build
Prep for Animal Study | Epic
Study previous experiments
Desing the Study protocol - especially probe placement
Freeze the software/hardware version and conduct final verification
Intellectual Property | Epic
Internal Innovation Review - ID potential new IP
Review pertinent prior art
Review prior art
Submit IP disclosure
Documentation
Build documentation package
Identify next potential partners
Conduct tranfer
Milestone
Non GLP Animal Study | Milestone | bar: 2027-03-25
GLP Animla Study | bar: 2027-06-17